| Phase | Duration (month) | Start (T0+) | End (T0+) | Activities | Payment Milestone (upon phase completion in %) | Payment Amount in EUR |
| --- | --- | --- | --- | --- | --- | --- |
| Site mobilization of the contractor | 6 | 0 | 6 | Schedule, Quality Plan (supplier and Major sub-suppliers), Inspection and Test Plan, List of subcontractors, Execution Design, construction methods, Material Specification Coordination lan, PPSPS, PRE and request for accesses of the contractor on site. Site Construction facilities (if any) installed. | 5 | To be added |
| B18 construction | 26 | 6 | 32 |  |  | To be added |
| Foundations & Basement |  |  |  |  | 10 |  |
| Superstructures |  |  |  |  | 15 |  |
| B20 Construction | 26 | 6 | 32 |  |  | To be added |
| Foundations & Basement |  |  |  |  | 10 |  |
| Superstructures |  |  |  |  | 15 |  |
| B63 Construction | 18 | 14 | 32 |  |  | To be added |
| Foundations & Basement |  |  |  |  | 10 |  |
| Superstructures |  |  |  |  | 10 |  |
| K2 Bridge | 12 | 6 | 18 |  |  | To be added |
| Foundations |  |  |  |  | 5 |  |
| Superstructures |  |  |  |  | 5 |  |
| K3 Bridge | 12 | 6 | 18 |  |  | To be added |
| Foundations |  |  |  |  | 5 |  |
| Superstructures |  |  |  |  | 5 |  |
| Rack S1 | 6 | 26 | 32 |  | 5 | To be added |
|  |  |  |  | Total Amount | 100% | To be added |